## Sheet1
Playbook Name |  | EMPLOYEE OFFBOARDING | * Playbook Items consist of Tasks, Touchpoints (Email/Calendar/Call), Automated Mails, NPS
Playbook Type |  | SCHEDULED | * Individual Items can be assigned to Any Role within the organization
Playbook Assignee |  | DIRECTOR - PEOPLE PRACTICE | * Individual Timelines are measured in Days from Inception for quick Assessment
Trigger Condition |  | KICK OFF 30 DAYS BEFORE EXIT | * Critical Tasks are called out to halt proceeding on rest of Playbook, in case this gets delayed
* Weightage allows true depiction of status, since each item cannot have equal importance
| Milestone | Task | Type | Assignee | Days from Inception | Critical (Yes/No) | Weightage
1 | INITIATION | Resignation Initiation: The team member initiates their resignation by sending an email or using the Keka platform | Task | Executive - People Practice | 1 | No | 2
2 | INITIATION | Exit Discussion: Set up 1-on-1 discussion with the team member and reporting manager to understand details and reason/ retention (as applicable) with the team member | Touchpoint | Director - People Practice | 1 | Yes | 7
3 | UPDATE | Post discussion, update and approve mutually agreed upon exit date on the Keka platform | Task | Executive - People Practice | 3 | Yes | 6
4 | PLANNING | Reporting Manager Transition: Collaborate with the relevant team member to facilitate a smooth transition of reporting manager for the employee, if applicable | Task | Executive - People Practice | 10 | No | 4
5 | PLANNING | Exit Guidelines and IT Proofs: Arrange a 1-on-1 call with the team member to discuss exit guidelines and IT proofs and share the details via email as well | Touchpoint | Director - People Practice | 16 | No | 5
6 | PLANNING | Exit Notifications: Issue an internal communication to the IT and Compliance teams, providing details of all exits for the current month to initiate asset recovery/data backup etc. | Task | Executive - People Practice | 25 | Yes | 9
7 | PLANNING | Follow-up: Connect with IT team to discuss plan for asset recovery and seek inputs on asset details (total assets/type/make/cost) | Task | Executive - People Practice | 27 | Yes | 7
8 | PLANNING | Send a follow-up reminder email on the day of exit for deactivation of accounts/access, asset recovery and data backup | Task | Executive - People Practice | 30 | Yes | 8
9 | CLOSURE | Share all exit and asset details for the current month with the Finance Head, specifically highlighting cases where asset recovery is applicable | Task | Director - People Practice | 30 | Yes | 9
10 | CLOSURE | Exit Processing and Data Removal: Following the exits for the current month, remove employee data from the SK Employee Insurance dashboard Plum | Task | Executive - People Practice | 31 | Yes | 6
11 | SETTLEMENT | FnF Processing and Payroll Integration: Process FnF settlements for exiting employees using Keka tool, aligning it with the monthly payroll | Task | Director - People Practice | 55 | Yes | 10
12 | SETTLEMENT | Exit Letter Generation: Use Keka tool to create Relieving, Experience, and Exit Statement letters for all exited employees after settlement pay-out | Task | Executive - People Practice | 60 | Yes | 7
13 | SETTLEMENT | Share all exit letters (Relieving/Experience/Exit Statement) with the employee to their personal mail IDs | Task | Executive - People Practice | 60 | Yes | 8