## Sheet1
Playbook Name |  | ACCOUNT RENEWAL | * Playbook Items consist of Tasks, Touchpoints (Email/Calendar/Call), Automated Mails, NPS
Playbook Type |  | AUTOMATED / SCHEDULED. | * Individual Items can be assigned to Any Role within the organization
Playbook Assignee |  | ACCOUNT MANAGER | * Individual Timelines are measured in Days from Inception for quick Assessment
Trigger Condition |  | Playbook Kick Off 45/60/75/90 days before Renewal Due. | * Critical Tasks are called out to halt proceeding on rest of Playbook, in case this gets delayed
* Weightage allows true depiction of status, since each item cannot have equal importance
| Milestone | Task | Type | Assignee | Days from Inception | Critical (Yes/No) | Weightage
1 | ASSESSMENT | Segmentation: Quickly check / validate which Customer Segment this client belongs to. | Task | Account Manager | 1 | No | 1
2 | ASSESSMENT | Assess Account Health: Evaluate account health based on factors such as customer engagement, product/service usage, relationship mapping and satisfaction. Share assessment with Account Manager. | Task | Customer Success Manager | 1 | No | 2
3 | ASSESSMENT | Review customer contract (to assess the deal details and if there are any upsell/ cross sell possibilities). Also evaluate expansion opportunities from product adoption and utilization data. | Task | Account Manager | 2 | No | 3
4 | ASSESSMENT | Assess Touchpoints: Check to validate regular check-ins with customers to assess their satisfaction, address concerns, and gather feedback. | Task | Account Manager | 3 | No | 2
5 | PRE PLAN | Proactively Address Issues: Address any identified issues or concerns before the renewal conversation to ensure customer satisfaction. Keep Account Manager informed when done. | Task | Customer Success Manager | 10 | Yes | 6
6 | PLANNING | Basis assessment, create a brief Renewal Plan (bullet points could do). Share the plan with all relevant stakeholder, and also add to "Account Notes' (if there is a location on platform to store) | Task | Account Manager | 10 | No | 2
7 | PLANNING | Prepare a Renewal Proposal: Create a tailored renewal proposal highlighting the value your product has provided, addressing any customer concerns, and explaining pricing and new opportunities for growth. | Task | Account Manager | 10 | No | 5
8 | PLANNING | List and communicate risks, if any. Risks can be any like shift in management at customer org, or poor adoption trend, etc. Should be communicated to all relevant stakeholders. | Touchpoint | Account Manager | 10 | No | 2
9 | CONTRACT | Communicate the Renewal Process: Clearly communicate the renewal process, timeline, and any changes in pricing or terms to the customer in a mail / meeting. | Touchpoint | Account Manager | 15 | No | 3
10 | CONTRACT | Send escalation mail internally if Customer showcases any doubts about Renewal, or when customer avoids communication on the subject. Gather stakeholders, make a plan to address, execute plan | Task | Account Manager | 20 | Yes | 10
11 | CONTRACT | Follow up 1 Meeting / Call - Engage in a transparent and open dialogue with the customer to negotiate the renewal terms and finalize the agreement. | Touchpoint | Account Manager | 25 | No | 5
12 | CONTRACT | Follow up 2 Meeting / Call (If required) - Final Contract Negotiations and Discussions. Keep Finance Manager informed of all details on what / when / how to proceed on the next step. | Touchpoint | Account Manager | 35 | No | 5
13 | CONTRACT | Send mail / details that will allow client to process payment. Ensure plans for the following year are communicated and payment is received. | Touchpoint | Finance Manager | 40 | Yes | 6
14 | CLOSURE | Review and Analyze Customer Feedback: Ensure customer feedback acquired in the process is shared with Account stakeholders and added to "Account Notes'. | Task | Customer Success Manager | 43 | No | 3
15 | CLOSURE | Review system to ensure that all contractual updates like users added, renewal info is appropriately updated, etc. | Task | Customer Success Manager | 46 | No | 2
16 | CLOSURE | Celebrate Success: Recognize and celebrate the successful renewal with your team to foster positive relationships and recognize great work at an appropriate juncture. | Task | Account Manager | 50 | No | 3