## Sales to CS handover Mid market
Playbook Name |  | Sales to CS Handover - Mid market | * Playbook Items consist of Tasks, Touchpoints (Email/Calendar/Call), Automated Mails, NPS
Playbook Type |  | AUTOMATED / SCHEDULED | * Individual Items can be assigned to Any Role within the organization
Playbook Assignee |  | ACCOUNT MANAGER/Sales rep | * Individual Timelines are measured in Days from Inception for quick Assessment
Trigger Condition |  | New Account created | * Critical Tasks are called out to halt proceeding on rest of Playbook, in case this gets delayed
* Weightage allows true depiction of status, since each item cannot have equal importance
| Milestone | Task | Type | Assignee | Days from Inception | Critical (Yes/No) | Weightage
1 | Post-Sale Handover | SR to schedule the kickoff call with the CSM and stakeholders. SR provides a comprehensive document with customer details, agreements, and implementation requirements for a seamless transition and successful onboarding. | Task | Sales Rep | 1 | No | 3
2 | Post-Sale Handover | CSM reviews the handover document and familiarizes themselves with the customer's needs, goals, and expectations. | Task | Customer Success Manager | 3 | No | 5
3 | Post-Sale Handover | SR to send an introductory email to the customer, introducing CSM and team and explaining their role as the dedicated point of contact. | Touchpoint | Sales Rep | 5 | No | 7
4 | Post-Sale Handover | SR schedules an initial onboarding call with the customer to discuss their onboarding process, timeline, and expectations. | Task | Sales Rep | 8 | No | 5
5 | Post-Sale Handover | CSM conducts the onboarding call, addressing any questions or concerns the customer may have and providing an overview of the onboarding plan. | Touchpoint | Customer Success Manager | 11 | Yes | 10
6 | Account Setup | CSM works with the internal technical team to ensure a smooth account setup and configuration. | Task | Implementation Manager | 14 | No | 8
7 | Account Setup | Conduct initial training sessions with the customer's key stakeholders, focusing on product features, functionality, and best practices. | Task | Implementation Manager | 17 | Yes | 9
8 | Account Setup | CSM follows up with an email summarizing the training session and providing additional resources or clarifications if needed. | Touchpoint | Customer Success Manager | 20 | No | 6
9 | Handover Review | SR and CSM schedule a joint call to review the handover process and discuss any lessons learned or areas for improvement. | Task | Sales Rep | 25 | No | 4
10 | Handover Review | SR and CSM exchange feedback and insights on the customer's journey from sales to CS. | Task | Sales Rep | 30 | No | 4

## Sales to CS handover Enterprise
Playbook Name |  | Sales to CS Handover - Enterprise | * Playbook Items consist of Tasks, Touchpoints (Email/Calendar/Call), Automated Mails, NPS
Playbook Type |  | AUTOMATED / SCHEDULED | * Individual Items can be assigned to Any Role within the organization
Playbook Assignee |  | ACCOUNT MANAGER/Sales rep | * Individual Timelines are measured in Days from Inception for quick Assessment
Trigger Condition |  | CRM Deal stage: Contract/ Closed-Won | * Critical Tasks are called out to halt proceeding on rest of Playbook, in case this gets delayed
* Weightage allows true depiction of status, since each item cannot have equal importance
| Milestone | Task | Type | Assignee | Days from Inception | Critical (Yes/No) | Weightage
1 | Deal Closure | Share Customer Information: Provide a comprehensive handover document containing customer details, contract information, and any specific requirements gathered during the sales process. | Task | Sales Rep | 1 | No | 3
2 | Deal Closure | Schedule Internal Meeting: Arrange a meeting with the Customer Success Manager (CSM), Implementation Specialist (if applicable), and other relevant team members. | Task | Sales Rep | 3 | No | 4
3 | Deal Closure | Identify milestones and timelines for achieving those goals. Ensure alignment between sales promises and customer expectations. | Task | Customer Success Manager | 7 | Yes | 5
4 | Initiate Engagement | Introduction Email: Send a personalized email to the customer, introducing yourself and the assigned CSM, implementation team, deidicated AM and Support | Touchpoint | Sales Rep | 12 | No | 3
5 | Initiate Engagement | Schedule Kickoff Call: Propose a time for a kickoff call to discuss the implementation plan in detail. | Task | Implementation Manager | 17 | Yes | 8
6 | Initiate Engagement | Provide updates on customization, configuration, or any ongoing implementation activities. | Touchpoint | Implementation Manager | 22 | No | 4
7 | Initiate Engagement | Adoption Monitoring: Monitor the customer's progress in adopting and utilizing the product. Include CSM, AM, Technical Support (if required) | Task | Sales Rep | 27 | No | 3
8 | Onboarding Progress | Identify any barriers to adoption and proactively address them. Offer guidance, training, or additional resources as needed. | Task | Customer Success Manager | 32 | No | 4
9 | Onboarding Progress | Review Handover Completion: Assess the customer's progress and satisfaction with the onboarding process. Include: CSM, SR, AM, Tech support, Implementation team, Product team and Exec. | Task | Sales Rep | 37 | No | 6
10 | Onboarding Progress | Confirm that key milestones and success criteria have been achieved. Address any outstanding issues or concerns. | Task | Customer Success Manager | 45 | Yes | 10
11 | Handover Review | CSM schedules a 1st QBR with the customer and SR to review their progress, ROI, and set goals for the upcoming quarter. | Task | Customer Success Manager | 60 | No | 9
12 | Handover Review | SR and CSM schedule a joint call to review the handover process and discuss any lessons learned or areas for improvement. | Task | Customer Success Manager | 70 | No | 6
13 | Handover Review | SR and CSM exchange feedback and insights on the customer's journey from sales to CS. | Touchpoint | Customer Success Manager | 80 | No | 5